## TaskDesk
Name | JIRA / TFS Ticket | Sprint No | Task Desc | Due date From | Due date to | Dev % Complete | Comments
Rama Narasimhulu | 2 |  | 1.Mandatory training section in ITC | 2021-10-08 | 16/08/2021 | 100% | 1. Complted Complaine mantadory trainings
|  |  | 2. Demo On Argo_POC | 17/08/2021 | 2021-10-09 | 50% | 2.1 Done research on the Argo_POC tool. 2.2 Face chanlleges to setup Argo tool. 2.3 Raised the request for dev Environment access in Black rock side. 2.4 After receving the access working on buliding POC.
Priyanka | 2 |  | 1.Mandatory training section in ITC | 2021-10-08 | 16/08/2021 | 100% | 1. Complted Complaine mantadory trainings
|  |  | 2.Demo On Airflow_POC | 17/08/2021 | 2021-10-09 | 50% | 2.1 Done research on the Airflow_POC. 2.2 Face chanlleges to setup Airflow tool. 2.3 Raised the request for dev Environment access in Black rock side. 2.4 After receving the access working on buliding POC

## AWSDE
Total number of tasks(Due dates 11/08/2021 - 17/09/2021)
Name | Total Assigned | In Progress | To Do | Completed | Missed Due Dates | Start Date | End Date
Rama | 2 | 1 | 0 | 1 | 0 | 2021-10-08 | 2021-10-09
Priyanka | 2 | 1 | 0 | 1 | 0 | 2021-10-08 | 2021-10-09